## Open tickets
Category | Category name | Ticket | Archived | Closed today | Title | Priority | State | Assignee | Four-suite evidence | Peter's review | Last activity | Waiting on / approval from | Note | Movement today
2 | Requires input | KS-486 |  |  | Review A — AuthN / AuthZ / tenancy & IDOR | P1 | In Review | Kam | PARTIAL (Sch·Akto·PW) | n/a | 2026-08-29 |  | Review A register — ours; split-out rows are separate tickets | reclassified 18:5x: bounced by s106 — its banner needs Kam's KS-621-class design ruling
1 | In our hands — ready to action | KS-670 |  | yes | P1 | Todo | Kam | n/a (no PR) | n/a | 2026-08-31 | Quota recovered (Kam upgraded); verify anchoring recovered, then close |  | CLOSED — Done (today)
3 | Done on our side — awaiting approval | KS-708 |  |  | Security: Akto ADD_USER_ID (BOLA, HIGH) on GET /api/platfor… | P1 | Backlog | — | n/a (no PR) | n/a | 2026-08-29 |  | Kam ruled Option B 2026-08-29; build it | moved — now In Review / Kam (08:47Z) · reclassified 18:5x: PR #783 on Peter (Option B built; amended after QA)
1 | In our hands — ready to action | KS-169 |  | yes | P2 | Backlog | Kam | n/a (no PR) | n/a | 2026-07-14 | — |  | CLOSED — Done (today)
1 | In our hands — ready to action | KS-214 |  | yes | P2 | Todo (archived) | — | PARTIAL (k6 — its own subject) | n/a | 2026-06-24 | Outstanding acceptance items; Stuart answered the auth-mode question (local sim) |  | CLOSED — Done (today)
1 | In our hands — ready to action | KS-229 |  |  | [Tracker] 2026-06-10 platform assurance review — gap-analys… | P2 | Backlog | — | n/a (no PR) | n/a | 2026-07-14 |  | —
1 | In our hands — ready to action | KS-256 |  |  | Add OpenAPI inline examples to all 329 operations — elimina… | P2 | In Review | Kam | FULL 2026-08-19 on old head; NOT run on custody rebase | n/a (Peter is author) | 2026-09-01 |  | Kam lifted the #568 hold 2026-09-02 (merge on a clean suite set); ours to run the four suites on the landing tree and merge | moved — now In Progress / Kam (07:30Z)
1 | In our hands — ready to action | KS-304 |  |  | Tokenise personal/identifying data — mint a privacy token (… | P2 | Backlog | Kam | UNKNOWN | NOT YET | 2026-07-14 |  | —
1 | In our hands — ready to action | KS-329 |  |  | Phase 2 — JWT RS256 → hybrid (RS256 + ML-DSA-65) | P2 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-12 |  | —
1 | In our hands — ready to action | KS-365 |  |  | Base-image refresh routine + track postgres CVE-2025-68121… | P2 | Backlog | Kam | UNKNOWN | NOT YET | 2026-08-14 |  | —
1 | In our hands — ready to action | KS-485 |  |  | Security review — plan, methodology & handover (Platform K) | P2 | Todo | Kam | n/a (no PR) | n/a | 2026-08-28 |  | —
1 | In our hands — ready to action | KS-487 |  |  | Review B — Input validation, injection, upload, XSS/SSRF &… | P2 | In Progress | Kam | FULL 2026-08-13 (CI fan-out on #683); #720 pending | CHANGES REQUESTED 08-31 (#720) | 2026-09-01 |  | Review B — Peter requested 5 changes on #720; ours to action
1 | In our hands — ready to action | KS-491 |  |  | Review F — Edge, WAF, DDoS & anti-automation | P2 | Todo | Kam | n/a (no PR) | n/a | 2026-08-18 |  | Remediated in code; live-edge verification not established
1 | In our hands — ready to action | KS-565 |  |  | Sweeps 2026-08-05: untracked failures across 10 ops — respo… | P2 | Backlog | Kam | n/a (no PR of its own) | n/a | 2026-09-01 |  | Sized L 09-01; not started
1 | In our hands — ready to action | KS-591 |  |  | positive_data_acceptance recurs at scale — 734 failures acr… | P2 | Backlog | Kam | n/a (no PR) | n/a | 2026-09-02 |  | Sized M 09-01; not started
1 | In our hands — ready to action | KS-593 |  |  | not_a_server_error recurs — 17 raw 5xx across 8 ops (KS-431… | P2 | Backlog | Kam | n/a (no PR of its own) | n/a | 2026-09-01 |  | Approach note ready; audit gate (#780) merged 09-01 23:18Z so pushes are unblocked
1 | In our hands — ready to action | KS-597 |  |  | Architecture P1: populate issuer_organization_id at registr… | P2 | Todo | Kam | n/a (no PR) | n/a | 2026-08-09 |  | —
1 | In our hands — ready to action | KS-598 |  |  | Architecture P1: defuse the MULTI_TENANCY registry upsert —… | P2 | Todo | Kam | n/a (no PR) | n/a | 2026-08-09 |  | —
1 | In our hands — ready to action | KS-601 |  |  | [Infra] New Platform K dev server "Kintsugi" — restore dev/… | P2 | In Progress | Kam | UNKNOWN | n/a | 2026-08-21 |  | Kintsugi in progress; §4 closed, name ratified
1 | In our hands — ready to action | KS-602 |  |  | BM-1: Certification model — certification = attestation + s… | P2 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-11 |  | —
1 | In our hands — ready to action | KS-603 |  |  | BM-2: Verification is a configurable workflow via smart con… | P2 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-11 |  | —
1 | In our hands — ready to action | KS-607 |  |  | GET /api/anchors/{id} and verify report different statuses… | P2 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-31 |  | Peter's gating question answered 08-12; investigation is ours
1 | In our hands — ready to action | KS-618 |  |  | Client IP is invisible platform-wide on demo: every IP-keye… | P2 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-13 |  | —
1 | In our hands — ready to action | KS-628 |  |  | CI: Performance suite fails on GHCR secondary rate limit wi… | P2 | Backlog | — | n/a (no PR) | n/a | 2026-08-17 |  | —
1 | In our hands — ready to action | KS-637 |  |  | Nightly Internal Audit has failed 40 runs straight — DAST,… | P2 | Backlog | — | n/a (no PR) | n/a | 2026-08-14 |  | —
1 | In our hands — ready to action | KS-638 |  |  | The extranet test board has never shown a green run — 0 pas… | P2 | Backlog | — | n/a (no PR) | n/a | 2026-08-14 |  | —
1 | In our hands — ready to action | KS-642 |  |  | Security: GET /api/keys enumerates another tenant's API key… | P2 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-26 |  | Likely superseded by KS-742 (deployed to UAT) — verify and close or re-scope
1 | In our hands — ready to action | KS-644 |  |  | Security: /api/events — ANY authenticated user reads every… | P2 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-16 |  | —
1 | In our hands — ready to action | KS-655 |  |  | KS-78 drift check is wrong three ways — reports 7 commits o… | P2 | Backlog | — | n/a (no PR) | n/a | 2026-08-17 |  | —
1 | In our hands — ready to action | KS-663 |  |  | The OpenAPI spec is now a consumed contract, but nothing in… | P2 | Todo | Kam | n/a (no PR) | n/a | 2026-08-29 |  | —
1 | In our hands — ready to action | KS-668 |  |  | Compose seeds published *123 credentials by default, and th… | P2 | Backlog | — | n/a (no PR) | n/a | 2026-08-24 |  | —
1 | In our hands — ready to action | KS-669 |  |  | Published spec points integrators at 18 URLs on domains we… | P2 | In Progress | — | UNKNOWN | n/a | 2026-08-21 |  | #725 merged; E1 rule gap + owner still open (17 URLs moved to KS-678)
1 | In our hands — ready to action | KS-676 |  |  | Two host scripts use bash 4 syntax and cannot run on macOS… | P2 | In Review | Kam | NONE (preflight only) | REVIEWED, no formal approval | 2026-08-21 |  | Peter: 'merge yours when you're happy' — merge is our action
1 | In our hands — ready to action | KS-677 |  |  | check-spec-examples is blind to path-parameter and scalar-p… | P2 | In Progress | Kam | n/a (no PR — rides #568) | n/a | 2026-09-01 |  | Fixed and pushed; new reproducible red (9→49) still ours | moved — now In Review / Kam (07:24Z)
1 | In our hands — ready to action | KS-683 |  |  | Anchor-status standoff: a consumer repolls anchors K report… | P2 | Todo | Kam | n/a (no PR) | n/a | 2026-08-31 |  | Stuart's layer 1 confirmed; K-side layers 3/4 remain
1 | In our hands — ready to action | KS-687 |  |  | Akto slot targeting: dump-result-fields.sh resolves the un-… | P2 | In Progress | Kam | UNKNOWN | APPROVED 08-27 (#732) | 2026-08-28 |  | #732 merged (F1); F2 half open and now unblocked
1 | In our hands — ready to action | KS-692 |  |  | Security: /api/status revoke/unrevoke has no tenant ownersh… | P2 | Backlog | Kam | n/a (no PR) | n/a | 2026-09-01 |  | —
1 | In our hands — ready to action | KS-693 |  |  | M365 routes answer 503 when ENTRA_* is unconfigured — 9 per… | P2 | Todo | Kam | n/a (no PR) | n/a | 2026-09-01 |  | —
1 | In our hands — ready to action | KS-695 |  |  | S↔K (K-side): erasure by external_ref, documents.title cove… | P2 | Todo | Kam | n/a (no PR) | n/a | 2026-09-01 |  | Stuart's side is finished and waiting on THIS ticket; design note + sizes posted 09-01
1 | In our hands — ready to action | KS-696 |  |  | Akto pr-scan is non-deterministic — three runs on near-iden… | P2 | Todo | Kam | n/a (no PR) | n/a | 2026-08-29 |  | —
1 | In our hands — ready to action | KS-698 |  |  | Security: one request permanently poisons any rate-limit ke… | P2 | Todo | Kam | n/a (no PR) | n/a | 2026-08-27 |  | —
1 | In our hands — ready to action | KS-707 |  |  | Playwright quality:static is RED again — .prettierignore na… | P2 | Backlog | — | n/a (no PR) | n/a | 2026-08-28 |  | —
1 | In our hands — ready to action | KS-709 |  |  | Akto reports a PASS for a test that executed NOTHING — 'cle… | P2 | Backlog | — | n/a (no PR) | n/a | 2026-08-29 |  | —
1 | In our hands — ready to action | KS-716 |  |  | The whole super-admin surface is silently unscanned — no sy… | P2 | Todo | Kam | n/a (no PR) | n/a | 2026-08-29 |  | —
1 | In our hands — ready to action | KS-720 |  |  | POST /api/auth/wallet/link and DELETE /unlink can never suc… | P2 | Todo | Kam | n/a (no PR) | n/a | 2026-08-31 |  | —
1 | In our hands — ready to action | KS-722 |  |  | Security: social sign-in never verifies the OAuth `state`,… | P2 | Todo | — | n/a (no PR) | n/a | 2026-08-29 |  | —
1 | In our hands — ready to action | KS-723 |  |  | Declare the remaining ~157 routed-but-undocumented /api ope… | P2 | Todo | — | n/a (no PR) | n/a | 2026-08-29 |  | —
1 | In our hands — ready to action | KS-724 |  |  | A scan that logs in more than ten times as one user revokes… | P2 | Todo | — | n/a (no PR) | n/a | 2026-08-29 |  | —
1 | In our hands — ready to action | KS-725 |  |  | test:pr never re-imports the OpenAPI spec, so Akto scans a… | P2 | Todo | — | n/a (no PR) | n/a | 2026-08-31 |  | —
1 | In our hands — ready to action | KS-729 |  |  | Upgrade ip-address off GHSA-mwp4-54f8-5fhr (high, SSRF) — e… | P2 | Todo | — | n/a (no PR) | n/a | 2026-09-01 |  | —
1 | In our hands — ready to action | KS-730 |  |  | Security: 71 inline handlers still return err.message verba… | P2 | Backlog | — | n/a (no PR) | n/a | 2026-08-31 |  | —
1 | In our hands — ready to action | KS-731 |  |  | Local slots share one Postgres/Redis credential pair — any… | P2 | Backlog | — | n/a (no PR) | n/a | 2026-09-01 |  | —
1 | In our hands — ready to action | KS-732 |  |  | Security: POST /api/auth/mfa/disable never verifies the pas… | P2 | Todo | — | n/a (no PR) | n/a | 2026-08-31 |  | —
1 | In our hands — ready to action | KS-733 |  |  | /api/users/me/mfa/* is unthrottled — the same TOTP surface… | P2 | Todo | — | n/a (no PR) | n/a | 2026-08-31 |  | —
1 | In our hands — ready to action | KS-734 |  |  | The e2e Playwright suite cannot run from a clean checkout —… | P2 | Todo | — | n/a (no PR) | n/a | 2026-08-31 |  | — | moved — now Todo / — (08:37Z)
1 | In our hands — ready to action | KS-735 |  |  | Verify results show the user nothing about what was registe… | P2 | Todo | — | n/a (no PR) | n/a | 2026-09-01 |  | —
1 | In our hands — ready to action | KS-737 |  |  | Platform-admin login skips MFA entirely when mfaCode is omi… | P2 | Todo | Kam | n/a (no PR) | n/a | 2026-09-01 |  | —
1 | In our hands — ready to action | KS-739 |  |  | transfer-custody maps a 401/403 from users/lookup to 502 BA… | P2 | Todo | — | n/a (no PR) | n/a | 2026-09-02 |  | Ruling received: build the 401/403 mapping fix; role/scope half stays with Kam
1 | In our hands — ready to action | KS-130 |  |  | Outlook add-in: add Platform S upload + corporate/domain de… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-06-16 |  | —
1 | In our hands — ready to action | KS-131 |  |  | Outlook add-in — Workstream A: Platform S functions (v1: up… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-06-10 |  | —
1 | In our hands — ready to action | KS-132 |  |  | Outlook add-in — Workstream B: corporate/M365 (domain) depl… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-05-25 |  | —
1 | In our hands — ready to action | KS-174 | yes |  | KS-160 Step 3: set tenant GUC on checkout + admin-role exem… | P3 | In Progress (archived) | — | UNKNOWN | n/a | 2026-06-03 |  | Stale In Progress since June; PR #191 — verify what landed, then close or resume
1 | In our hands — ready to action | KS-242 |  |  | Euro Office (office.eu) connector — joint Platform K + Plat… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-06-10 |  | —
1 | In our hands — ready to action | KS-243 |  |  | [Marketing] Euro Office (office.eu) connector — go-to-marke… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-06-10 |  | —
1 | In our hands — ready to action | KS-247 |  |  | [Pre-mainnet] State-thread NFT — Sprint 2 Phase 2 (on-chain… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-06-10 |  | —
1 | In our hands — ready to action | KS-248 |  |  | [Pre-mainnet] Replace stub ZK proof provider with a real pr… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-06-10 |  | —
1 | In our hands — ready to action | KS-287 |  |  | [Dev] deploy.sh setup doesn't fully provision a fresh regio… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-08-14 |  | —
1 | In our hands — ready to action | KS-305 |  |  | State the M365 source-document controller boundary in the c… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-07-14 |  | —
1 | In our hands — ready to action | KS-330 |  |  | Phase 3 — Issuer certs + VC PQC signing (ML-DSA, dual-sign) | P3 | Backlog | — | n/a (no PR) | n/a | 2026-06-25 |  | —
1 | In our hands — ready to action | KS-332 |  |  | Resolve PQC migration dependencies / decisions | P3 | Backlog | — | n/a (no PR) | n/a | 2026-06-25 |  | —
1 | In our hands — ready to action | KS-354 |  |  | [start-secuura.sh --rebuild] Multi-arch image builds for am… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-07-14 |  | —
1 | In our hands — ready to action | KS-373 | yes |  | Aiken stdlib v2.2.0 → v3.1.0 (breaking) — needs contract-co… | P3 | Backlog (archived) | — | n/a (no PR) | n/a | 2026-07-14 |  | Archived 07-16 in Backlog; needs contract-context review
1 | In our hands — ready to action | KS-408 |  |  | boot-platform-stack: assert no container is restart-looping… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-08-14 |  | —
1 | In our hands — ready to action | KS-409 |  |  | Express 4 → 5 migration (all 15 services) — dependabot #447… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-08-14 |  | —
1 | In our hands — ready to action | KS-410 |  |  | @types wave: @types/node 26 vs Node 24 runtime — dependabot… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-08-14 |  | —
1 | In our hands — ready to action | KS-411 |  |  | TypeScript 5 → 6 migration (all packages) — dependabot #428… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-08-14 |  | —
1 | In our hands — ready to action | KS-483 |  |  | Extend Prettier + knip quality tooling from into the base t… | P3 | Todo | Kam | n/a (no PR) | n/a | 2026-08-27 |  | —
1 | In our hands — ready to action | KS-526 |  |  | KMS: move platform wallet mnemonic to Key Vault (KS-326 fol… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-07-25 |  | —
1 | In our hands — ready to action | KS-528 |  |  | Frontends: react-router v6 → v7 migration (3 moderate clien… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-14 |  | —
1 | In our hands — ready to action | KS-530 |  |  | @hono/node-server v1->v2 major bump (GHSA-frvp) - originate… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-08-14 |  | —
1 | In our hands — ready to action | KS-541 |  |  | Proposal: smart-contract cascading governance hierarchy for… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-07-31 |  | —
1 | In our hands — ready to action | KS-542 |  |  | Document encryption phase 2: personal + organisational keys… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-07-31 |  | —
1 | In our hands — ready to action | KS-553 |  |  | arm64 GHCR images for the demo VM — compose pull instead of… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-02 |  | —
1 | In our hands — ready to action | KS-562 |  |  | anchoring threadTokenMint test fails only under root-visibl… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-08-26 |  | —
1 | In our hands — ready to action | KS-567 |  |  | CI: GHCR secondary-rate-limit kills deps-changed PR runs —… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-05 |  | —
1 | In our hands — ready to action | KS-578 |  |  | Cross-tenant API-key revoke misses the DB row when the cach… | P3 | In Review | Kam | NONE (#744 not run) | APPROVED (#744 merged 09-01) | 2026-09-01 |  | Approach note ready, no code yet (revoke not durable); ours to build
1 | In our hands — ready to action | KS-579 |  |  | Per-person platform-admin identities — the shared seeded ad… | P3 | Todo | Kam | n/a (no PR) | n/a | 2026-08-26 |  | —
1 | In our hands — ready to action | KS-580 |  |  | Append-only recovery audit held outside the estate being re… | P3 | Todo | Kam | n/a (no PR) | n/a | 2026-08-26 |  | —
1 | In our hands — ready to action | KS-581 |  |  | register-connector: volume alerting, rate limit, and correl… | P3 | Todo | Kam | n/a (no PR) | n/a | 2026-08-26 |  | —
1 | In our hands — ready to action | KS-583 |  |  | DR rehearsal: lose a key → re-key → read-back survives on p… | P3 | Todo | Kam | n/a (no PR) | n/a | 2026-08-07 |  | —
1 | In our hands — ready to action | KS-595 |  |  | Three undeclared-verb catalogue skips cite CLOSED tickets (… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-19 |  | Remaining: measure whether the three undeclared-verb defects are live
1 | In our hands — ready to action | KS-604 |  |  | BM-5: System-details document for Peter & Stuart — the tech… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-11 |  | —
1 | In our hands — ready to action | KS-605 |  |  | Terminology definitions for stakeholders + lawyers — certif… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-11 |  | —
1 | In our hands — ready to action | KS-619 |  |  | Gateway tenant resolution falls through to the caller's x-t… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-14 |  | —
1 | In our hands — ready to action | KS-621 |  |  | Document reads are scoped by tenant and owner, never by org… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-27 |  | —
1 | In our hands — ready to action | KS-625 |  |  | /presentations/verify reports a presentation verified witho… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-13 |  | —
1 | In our hands — ready to action | KS-626 |  |  | Entra Verified-ID callback is unreachable two ways: registe… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-08-13 |  | —
1 | In our hands — ready to action | KS-627 |  |  | Implement real wallet signature verification (CIP-8/COSE +… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-08-26 |  | —
1 | In our hands — ready to action | KS-629 |  |  | kyc `livenessVideo` is accepted by spec and runtime, then s… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-08-13 |  | —
1 | In our hands — ready to action | KS-630 |  |  | Wire the status-page XSS probe into preflight (or decide no… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-08-14 |  | —
1 | In our hands — ready to action | KS-633 | yes |  | billing/chargeable-events.ts is a dead parallel metering im… | P3 | Backlog (archived) | Kam | n/a (no PR) | n/a | 2026-08-13 |  | Archived 08-21 in Backlog (issue-cap cull)
1 | In our hands — ready to action | KS-650 |  |  | services/originate: POST /api/webhooks 500s on its two succ… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-09-01 |  | Open question answered (stale fixture); fix the fixture
1 | In our hands — ready to action | KS-658 |  |  | The demo VM runs every service as NODE_ENV=development whil… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-08-31 |  | —
1 | In our hands — ready to action | KS-682 |  |  | Playwright keeps no run history — a re-run on the same slot… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-08-21 |  | —
1 | In our hands — ready to action | KS-699 |  |  | No table references `users`: 0 of the database's 29 foreign… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-27 |  | —
1 | In our hands — ready to action | KS-704 |  |  | k6 gate reports a failure rate with no status-code breakdow… | P3 | Todo | Kam | n/a (no PR) | n/a | 2026-08-27 |  | —
1 | In our hands — ready to action | KS-736 |  |  | Gateway mount-auth check scores authenticateToken(false) as… | P3 | Todo | Kam | n/a (no PR) | n/a | 2026-09-02 |  | —
1 | In our hands — ready to action | KS-738 |  |  | schemathesis run.py bootstrap can os.execv-loop forever on… | P3 | Todo | — | n/a (no PR) | n/a | 2026-09-01 |  | —
1 | In our hands — ready to action | KS-741 |  |  | x-emitter-internal is unstripped on the /originate/ route —… | P3 | Todo | Kam | n/a (no PR) | n/a | 2026-09-01 |  | —
1 | In our hands — ready to action | KS-745 |  |  | api-gateway audit export calls /api/audit/logs — a route th… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-09-01 |  | —
1 | In our hands — ready to action | KS-746 |  |  | Security events carry no tenant at all — KS-743 had to gate… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-09-01 |  | —
1 | In our hands — ready to action | KS-747 |  |  | Spec drift: GET /api/security/keys declares no parameters w… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-09-01 |  | —
1 | In our hands — ready to action | KS-750 |  |  | api-gateway + originate keep their own error handlers inste… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-09-01 |  | —
1 | In our hands — ready to action | KS-306 |  |  | Decide + promote the Art.17 DPIA note into the formal DPIA… | P4 | Backlog | Kam | n/a (no PR) | n/a | 2026-07-14 |  | —
1 | In our hands — ready to action | KS-331 |  |  | Phase 4 — Decommission classical paths + residual-risk regi… | P4 | Backlog | — | n/a (no PR) | n/a | 2026-06-25 |  | —
1 | In our hands — ready to action | KS-339 |  |  | Grant Phil + Steve extranet access (evolve toward company s… | P4 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-14 |  | —
1 | In our hands — ready to action | KS-353 |  |  | [start-secuura.sh --rebuild] Clear npm dependency deprecati… | P4 | Backlog | — | n/a (no PR) | n/a | 2026-08-14 |  | —
1 | In our hands — ready to action | KS-371 | yes |  | PostgreSQL 15 → 18 (compose + bicep + demo Flexible Server… | P4 | Backlog (archived) | — | n/a (no PR) | n/a | 2026-07-14 |  | Archived 07-16 in Backlog; no owner
1 | In our hands — ready to action | KS-403 |  |  | boot-platform-stack composite action reads BUILD_TAG/STACK_… | P4 | Backlog | — | n/a (no PR) | n/a | 2026-08-14 |  | —
1 | In our hands — ready to action | KS-422 |  |  | flutter-verify-app: align Android Gradle/AGP toolchain with… | P4 | Backlog | Kam | n/a (no PR) | n/a | 2026-07-14 |  | —
1 | In our hands — ready to action | KS-456 |  |  | Optional: expose per-process Node heap/RSS metrics (light u… | P4 | Backlog | Kam | n/a (no PR) | n/a | 2026-07-14 |  | —
1 | In our hands — ready to action | KS-623 |  |  | Test-token env guard is asymmetric: the gateway fails close… | P4 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-13 |  | —
1 | In our hands — ready to action | KS-648 |  |  | Frontend CSP quality: issuer alone carries 'unsafe-eval', a… | P4 | Backlog | — | n/a (no PR) | n/a | 2026-08-17 |  | —
1 | In our hands — ready to action | KS-681 |  |  | Launcher drift warning counts HEAD but reports "on main" —… | P4 | Todo | Kam | n/a (no PR) | n/a | 2026-09-01 |  | —
1 | In our hands — ready to action | KS-690 |  |  | scripts/check-test-wallet-testnet.sh has zero callers — wir… | P4 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-26 |  | —
1 | In our hands — ready to action | KS-744 |  |  | Gateway 500s on every proxied route for a token lacking ver… | P4 | Backlog | — | n/a (no PR) | n/a | 2026-09-01 |  | —
1 | In our hands — ready to action | KS-748 |  |  | svc_api_keys.organization_id is not a tenancy boundary and… | P4 | Backlog | — | n/a (no PR) | n/a | 2026-09-01 |  | —
1 | In our hands — ready to action | KS-749 |  |  | postcss-selector-parser 6.1.2 carries GHSA-w9m9-85wc-3x92 —… | P4 | Backlog | — | n/a (bump not started) | n/a | 2026-09-01 |  | The dependency bump itself; #780 (baseline) merged 09-01
2 | Requires input | KS-740 |  |  | POST /api/timestamps/batch cannot serve its own documented… | — | Backlog | Kam | n/a (no PR) | n/a | 2026-09-01 |  | — | moved — now Backlog / Kam (08:46Z) · reclassified 18:5x: measured + mechanism named; the fix decision is Kam's card
2 | Requires input | KS-441 |  |  | Akto CI scan throughput: ~21 s local vs ~10 min in the isol… | P1 | Blocked | Peter | PARTIAL (Akto·Sch) | n/a | 2026-08-28 | Peter | Peter's ticket; post-merge review list recorded, not actioned
2 | Requires input | KS-608 |  |  | systemTest (Integration mode): GET /api/anchors/{id} and ve… | P1 | Blocked | Peter | n/a (no PR) | n/a | 2026-08-28 | Peter | Peter's ticket, Blocked
2 | Requires input | KS-660 |  |  | CI: every `needs: build` suite job dies in 3s with ZERO ste… | P1 | Blocked | — | UNKNOWN | NOT YET | 2026-09-01 | Kam (money) | Blocked on a money decision with a date (GitHub Actions org spend)
2 | Requires input | KS-61 |  |  | OpenAPI compliance: documentation gaps across the spec (des… | P2 | Todo | Stuart | n/a (no PR) | n/a | 2026-08-28 | Stuart | Assigned to Stuart (his work)
2 | Requires input | KS-62 |  |  | OpenAPI Specification Compliance: Optional Features | P2 | In Review | Stuart | PARTIAL (Akto·Sch 08-12) | n/a | 2026-08-28 | Stuart (sign-off) | Stuart's ticket; #670 merged, example legs need Stuart's sign-off
2 | Requires input | KS-188 |  |  | Stateful testing: declare OpenAPI `links` + `operationId` s… | P2 | Todo | Stuart | n/a (no PR) | n/a | 2026-08-28 | Stuart | Assigned to Stuart (his work)
2 | Requires input | KS-232 |  |  | Enable Postgres HA + geo-redundant backups + extend retenti… | P2 | Backlog | — | n/a (no PR) | n/a | 2026-08-12 | Kam (re-scope) | Deferred to commercialisation by Kam 2026-06-23; target resource no longer exists — needs re-scope
2 | Requires input | KS-239 |  |  | [Decision] Erasure: multi-step to trigger, but irreversible… | P2 | Backlog | Stuart | n/a (no PR) | n/a | 2026-08-12 | Stuart | Assigned to Stuart (his work)
2 | Requires input | KS-246 |  |  | [Pre-mainnet] External Aiken-specialist smart-contract audi… | P2 | Backlog | — | n/a (no PR) | n/a | 2026-08-14 | Kam (money, mainnet date) | Parked: needs budget + a mainnet date
2 | Requires input | KS-386 |  |  | KYC image payloads (svc_kyc_images.data) are plaintext at r… | P2 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-12 | Kam + compliance (Stuart) | KYC image retention is a compliance question; options a/b/c await ruling
2 | Requires input | KS-412 |  |  | CI: require all systemTest (all tools) PR suites + pre-merg… | P2 | Todo | Peter | n/a (no PR) | n/a | 2026-08-15 | Peter | Assigned to Peter (his work)
2 | Requires input | KS-489 |  |  | Review D — Blockchain / anchoring / smart-contract integrity | P2 | In Review | Kam | PARTIAL (Sch·Akto) | n/a | 2026-08-31 | Kam (prism scope ruling) | Review D register; the prism delete-vs-implement choice is Kam's
2 | Requires input | KS-525 |  |  | Playwright: end-to-end flow coverage across all 310 publish… | P2 | Backlog | Peter | n/a (no PR) | n/a | 2026-07-25 | Peter | Assigned to Peter (his work)
2 | Requires input | KS-568 |  |  | systemTest (Schemathesis): S↔K connector identity regressio… | P2 | Backlog | Peter | n/a (no PR) | n/a | 2026-08-07 | Peter | Assigned to Peter (his work)
2 | Requires input | KS-575 |  |  | Schemathesis sweep locks itself out of its own account (dem… | P2 | In Progress | Peter | UNKNOWN | NOT YET | 2026-08-25 | Peter | Assigned to Peter (his work)
2 | Requires input | KS-576 |  |  | Bulk re-key: one admin-authorised rotate across a named set… | P2 | Todo | Kam | n/a (no PR) | n/a | 2026-09-02 | Kam (rule on Stuart's proposal) | Stuart's grant-driven re-key proposal (2026-09-02) needs a ruling
2 | Requires input | KS-577 |  |  | rotate: true mints a new key but never revokes the old one… | P2 | Todo | Kam | n/a (no PR) | n/a | 2026-08-26 | Stuart (decision) | Contract decision on in-flight writes at revoke is Stuart's
2 | Requires input | KS-588 |  |  | systemTest (Schemathesis): /api/status authorization + revo… | P2 | Backlog | Peter | n/a (no PR) | n/a | 2026-08-28 | Peter | Assigned to Peter (his work)
2 | Requires input | KS-590 |  |  | systemTest (Schemathesis): verify-by-hash must not resolve… | P2 | Backlog | Peter | n/a (no PR) | n/a | 2026-08-12 | Peter | Assigned to Peter (his work)
2 | Requires input | KS-592 |  |  | negative_data_rejection recurs — 176 failures across 10 ops… | P2 | In Review | Kam | n/a (no fix PR) | n/a | 2026-09-01 | Kam (KS-662 ruling) | Remaining work is a ruling (split accepted-invalid vs permissive; sequence KS-662 first)
2 | Requires input | KS-624 |  |  | prism issues VCs with random bytes as the Ed25519 proof and… | P2 | Backlog | Kam | n/a (no PR) | n/a | 2026-08-13 | Kam (ruling) | Awaits Kam's ruling on prism's credential surface (KS-489 scope)
2 | Requires input | KS-634 |  |  | No CI gate runs the services' unit suites — a 73-test suite… | P2 | Backlog | — | n/a (no PR) | n/a | 2026-08-17 | Kam (routing) | Duplicate pair with KS-652; which survives is on Kam's routing queue
2 | Requires input | KS-636 |  |  | node:24-alpine carries a CRITICAL (CVE-2026-59873) — our ow… | P2 | Backlog | — | n/a (no PR) | n/a | 2026-08-15 | Kam (decide / authorise dispatch) | Evidence gathered; dispatching the shared CI watch / deciding is out of agent scope
2 | Requires input | KS-652 |  |  | No CI job runs any services/* unit suite — 1219 tests acros… | P2 | Backlog | — | n/a (no PR) | n/a | 2026-08-17 | Kam (routing) | Duplicate pair with KS-634; which survives is on Kam's routing queue
2 | Requires input | KS-665 |  |  | KS-256 review follow-ups: 5 example-fixable 400s, the tsx t… | P2 | In Progress | Kam | n/a (no PR) | n/a | 2026-08-21 | Peter (agree design) + #568 landing | Item-2 fixture design posted for agreement; held until #568 lands
2 | Requires input | KS-685 |  |  | Define the work → test → commit → manual-merge process whil… | P2 | In Review | Stuart | FULL 2026-08-28 (post-merge SET on develop) | APPROVED 08-28 (#749/#751 at-head) | 2026-08-29 | Stuart (own the doc) | Stuart's process write-up; our evidence posted
2 | Requires input | KS-691 |  |  | Pre-push preflight cannot run from a git worktree — legs 1… | P2 | In Review | Peter | PARTIAL (Akto x4 slots + unit, 09-01) | n/a (author) | 2026-09-01 | Peter (draft → ready) | Peter's own fix, draft PR #765
2 | Requires input | KS-717 |  |  | Akto test-id catalog and the loaded template library drift… | P2 | In Progress | Peter | UNKNOWN | NOT YET | 2026-08-29 | Peter | Assigned to Peter (his work)
2 | Requires input | KS-101 |  |  | Consolidate Platform K billing onto Platform S's Stripe int… | P3 | Backlog | Stuart | n/a (no PR) | n/a | 2026-07-14 | Stuart | Assigned to Stuart (his work)
2 | Requires input | KS-135 |  |  | Platform S "S+" refactor — pluggable upload/watermark/sign/… | P3 | Todo | Stuart | n/a (no PR) | n/a | 2026-05-28 | Stuart | Assigned to Stuart (his work)
2 | Requires input | KS-139 |  |  | Platform S — upload your test suite so the extranet live ru… | P3 | Backlog | Stuart | n/a (no PR) | n/a | 2026-08-14 | Stuart | Assigned to Stuart (his work)
2 | Requires input | KS-227 | yes |  | Schemathesis: Gate CI/CD on no-test-cases skips once schema… | P3 | Backlog (archived) | Peter | n/a (no PR) | n/a | 2026-06-24 | Peter | Assigned to Peter; archived 07-16
2 | Requires input | KS-263 |  |  | Enable Code Security / GHAS so security scans populate the… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-08-14 | Kam / GitHub org admin | GHAS/Code Security is an org-level GitHub setting (licensing)
2 | Requires input | KS-378 |  |  | Go-live login capacity decision: argon2 budget × per-IP lim… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-07-14 | Kam (decision) | Explicit go-live capacity decision ticket
2 | Requires input | KS-418 |  |  | systemTest (all tools): enable nightly platform test suites… | P3 | Todo | Peter | UNKNOWN | NOT YET | 2026-08-14 | Peter | Assigned to Peter (his work)
2 | Requires input | KS-492 |  |  | Review G — systemTest (all tools) security regression cover… | P3 | In Progress | Peter | FULL 2026-08-16 (CI fan-out) | n/a | 2026-08-28 | Peter | Peter's standing Review-G tracker
2 | Requires input | KS-502 |  |  | systemTest (Schemathesis): skipped security regressions nee… | P3 | Todo | Peter | n/a (no PR) | n/a | 2026-08-24 | Peter | Assigned to Peter (his work)
2 | Requires input | KS-533 |  |  | S↔K security register: data-loss / unrecoverability scenari… | P3 | Todo | Peter | n/a (no PR) | n/a | 2026-08-27 | Peter | Assigned to Peter (his work)
2 | Requires input | KS-545 |  |  | Rotate demo Cardano wallet mnemonic — GATED: do just before… | P3 | Backlog | Kam | n/a (no PR) | n/a | 2026-07-31 | Kam (go-live date) | Gated: rotate just before go-live
2 | Requires input | KS-571 |  |  | systemTest (Schemathesis): KS-539 agent document-operation… | P3 | Backlog | Peter | n/a (no PR) | n/a | 2026-08-19 | Peter | Assigned to Peter (his work)
2 | Requires input | KS-572 |  |  | systemTest (Schemathesis): pin the KS-546 unhandledRejectio… | P3 | Backlog | Peter | n/a (no PR) | n/a | 2026-08-07 | Peter | Assigned to Peter (his work)
2 | Requires input | KS-573 |  |  | systemTest (Schemathesis): assert the shared control-byte b… | P3 | Todo | Peter | UNKNOWN | NOT YET | 2026-08-07 | Peter | Assigned to Peter (his work)
2 | Requires input | KS-582 |  |  | [Decision] Approval shape for bulk re-key — two approvers f… | P3 | Todo | Kam | n/a (no PR) | n/a | 2026-09-02 | Kam + Stuart | [Decision] approval shape; Stuart's 2026-09-02 proposal reshapes it
2 | Requires input | KS-606 |  |  | systemTest (Schemathesis): split scripts/run.py + scripts/r… | P3 | Backlog | Peter | n/a (no PR) | n/a | 2026-08-12 | Peter | Assigned to Peter (his work)
2 | Requires input | KS-651 |  |  | [Decision] @secuura/shared is imported by 24 services and d… | P3 | Backlog | — | n/a (no PR) | n/a | 2026-08-17 | Kam (decision) | Explicit [Decision] ticket
2 | Requires input | KS-657 |  |  | services/shared (@secuura/service-utils) cannot build — no… | P3 | In Review | — | PARTIAL (Sch·Akto 08-17) | NOT YET | 2026-08-17 | Kam (decision, with KS-651) | Build half merged (#717); the retire/keep decision for services/shared is open
2 | Requires input | KS-679 |  |  | Published Anchor.id is anc_… but anchoring only ever mints… | P3 | Todo | Kam | n/a (no PR) | n/a | 2026-08-21 | Kam (release hold) | Held deliberately on Kam's word (left in Todo on purpose)
2 | Requires input | KS-686 |  |  | not_a_server_error flags the by-design 501 on POST /api/wal… | P3 | Backlog | Peter | n/a (no PR) | n/a | 2026-08-26 | Peter (land guard) | Kam ruled 2026-08-26 (tolerate 501); Peter lands the guard
2 | Requires input | KS-341 |  |  | KS-327 follow-up — get X25519MLKEM768 PQ hybrid live on the… | P4 | Backlog | — | n/a (no PR) | n/a | 2026-08-14 | Kam (domain / re-decision) | Deferred per Kam 2026-06-27; no owned domain; premise now dead — needs re-decision
3 | Done on our side — awaiting approval | KS-563 | yes |  | Verify API: isCertified is true for merely-anchor… | P1 | Deployed to UAT (archived) | Kam | UNKNOWN | not evidenced | 2026-08-14 | Kam/Stuart (UAT accept) | On demo since the 08-14 Kintsugi deploy; archived 08-14
3 | Done on our side — awaiting approval | KS-584 | yes |  | Verify by hash selects the wrong registration: ce… | P1 | Deployed to UAT (archived) | Kam | UNKNOWN | not evidenced | 2026-08-19 | Kam (close) | Live on demo; Stuart confirmed from Platform S 08-19
3 | Done on our side — awaiting approval | KS-667 |  |  | KS-311 regressed on fresh deploys: migration 033… | P1 | In Review | Kam | NONE (preflight only) | APPROVED 09-01 | 2026-09-01 | Kam (deploy / accept) | #726 + #772 merged on Peter's at-head approval 09-01
3 | Done on our side — awaiting approval | KS-694 | yes |  | Security: GDPR DSR list + deletion log have NO ro… | P1 | Deployed to UAT (archived) | Kam | FULL 2026-08-28 (SET on develop, KS-685) | APPROVED 08-28 (relayed set) | 2026-08-31 | Kam/Stuart (UAT accept) | #747 merged + deployed to demo 08-28, edge-verified
3 | Done on our side — awaiting approval | KS-697 | yes |  | transfer-custody accepts a NON-EXISTENT holder id… | P1 | Deployed to UAT (archived) | Kam | FULL 2026-08-28 (SET on develop, KS-685) | APPROVED 08-28 11:55Z | 2026-08-28 | Kam/Stuart (UAT accept) | #751 merged + deployed to demo 08-28
3 | Done on our side — awaiting approval | KS-63 | yes |  | Playwright: Phase 1: Sub-Issue 7: Install, Config… | P2 | In Review (archived) | Peter | UNKNOWN | n/a (Peter's) | 2026-06-24 | Peter (close) | #316 merged 06-23; Peter's ticket
3 | Done on our side — awaiting approval | KS-244 | yes |  | [Decision] Platform K billing — token / transacti… | P2 | In Review (archived) | Stuart | n/a (decision) | n/a | 2026-08-11 | Stuart (close) | Decision settled 06-23/08-03; archived as actioned
3 | Done on our side — awaiting approval | KS-490 |  |  | Review E — Deployment, containers & CI/CD supply… | P2 | Todo | Kam | n/a (review) | n/a | 2026-08-17 | Kam (close) | Review E fully dispositioned and re-verified 08-17
3 | Done on our side — awaiting approval | KS-537 | yes |  | document_lifecycle_events.payload stores PII unen… | P2 | Deployed to UAT (archived) | Kam | UNKNOWN | not evidenced | 2026-08-14 | Kam/Stuart (UAT accept) | On demo since the 08-14 Kintsugi deploy; archived 08-14
3 | Done on our side — awaiting approval | KS-543 | yes |  | certification erasure is cosmetic: events stamp a… | P2 | Deployed to UAT (archived) | Kam | UNKNOWN | not evidenced | 2026-08-14 | Kam/Stuart (UAT accept) | On demo since the 08-14 Kintsugi deploy; archived 08-14
3 | Done on our side — awaiting approval | KS-564 | yes |  | /share, /lifecycle-events and /certifications/iss… | P2 | Deployed to UAT (archived) | Kam | UNKNOWN | not evidenced | 2026-08-14 | Kam/Stuart (UAT accept) | On demo since the 08-14 Kintsugi deploy; archived 08-14
3 | Done on our side — awaiting approval | KS-566 |  |  | KS-539 G-1 split alignment: add onBehalfOf to rev… | P2 | In Review | Kam | UNKNOWN | APPROVED 09-01 (#742) | 2026-09-02 | Stuart (PS-616 reconcile) then close | Code DONE and MERGED (#742, approved by Peter 09-01); Kam ruled 'ask Stuart first' on the ownership gate | moved — now In Review / Kam (07:15Z)
3 | Done on our side — awaiting approval | KS-570 |  |  | GET /api/status + /api/leaderboard/* accept revok… | P2 | In Review | Kam | PARTIAL (Akto red-run by Peter; deterministic probe) | REVIEWED, blocker cleared 09-01 | 2026-09-01 | Peter (approve/merge) | PR #730; Peter's 08-31 blocker cleared, run posted at 3fe1b6f1a
3 | Done on our side — awaiting approval | KS-587 | yes |  | 84 demo anchors carry mock_tx_ hashes but are fla… | P2 | Deployed to UAT (archived) | Kam | UNKNOWN | not evidenced | 2026-08-14 | Kam/Stuart (UAT accept) | On demo since the 08-14 Kintsugi deploy; archived 08-14
3 | Done on our side — awaiting approval | KS-594 | yes |  | Governance active-proposal cap returns 500 INTERN… | P2 | Deployed to UAT (archived) | Kam | UNKNOWN | not evidenced | 2026-08-14 | Kam/Stuart (UAT accept) | On demo since the 08-14 Kintsugi deploy; archived 08-14
3 | Done on our side — awaiting approval | KS-613 | yes |  | The live gateway conf has no rate-limit, body cap… | P2 | Deployed to UAT (archived) | Kam | UNKNOWN | not evidenced | 2026-08-14 | Kam/Stuart (UAT accept) | On demo since the 08-14 Kintsugi deploy; archived 08-14
3 | Done on our side — awaiting approval | KS-614 | yes |  | Postgres and Redis listen on 0.0.0.0 on the demo… | P2 | Deployed to UAT (archived) | Kam | UNKNOWN | not evidenced | 2026-08-14 | Kam/Stuart (UAT accept) | On demo since the 08-14 Kintsugi deploy; archived 08-14
3 | Done on our side — awaiting approval | KS-617 | yes |  | A brief Redis outage latches auth/api-gateway/ori… | P2 | Deployed to UAT (archived) | Kam | UNKNOWN | not evidenced | 2026-08-14 | Kam/Stuart (UAT accept) | On demo since the 08-14 Kintsugi deploy; archived 08-14
3 | Done on our side — awaiting approval | KS-635 |  |  | Audit baseline exception expires 2026-08-31 and w… | P2 | In Review | Kam | NONE (preflight only) | APPROVED 09-01 | 2026-09-01 | Kam (merge-set); then close | #738; Peter approved 09-01 07:43Z (recorded on KS-729)
3 | Done on our side — awaiting approval | KS-641 |  |  | demo-service has no inbound auth — POST /demo-api… | P2 | In Review | Kam | NONE (preflight only) | REQUESTED | 2026-09-01 | Peter; then Kam (deploy) | PR #737 up; deploy precondition recorded
3 | Done on our side — awaiting approval | KS-643 |  |  | Security: DELETE /api/keys/:id revokes any tenant… | P2 | In Review | Kam | NONE (#744: not run) | APPROVED 09-01 | 2026-09-01 | Kam (deploy / accept) | #744 + #771 merged 09-01 on Peter's at-head approval
3 | Done on our side — awaiting approval | KS-661 |  |  | Rename the `certify` lifecycle verb to `declare` | P2 | In Review | Kam | NONE (preflight legs skipped) | n/a (Stuart approved #736) | 2026-08-27 | Stuart (S switches verb) then close | K half deployed to demo 08-26; PS-612 pinged
3 | Done on our side — awaiting approval | KS-664 |  |  | deepmerge-ts GHSA-ggr8-5vv4-36mx (high) — overrid… | P2 | In Progress | Kam | UNKNOWN | n/a (Peter's fix) | 2026-08-26 | Peter (close) | Fix merged via #725; Peter's ticket to close (baseline row stays)
3 | Done on our side — awaiting approval | KS-671 |  |  | anchoring /health reports 'healthy' with a dead c… | P2 | In Review | Kam | UNKNOWN | NOT YET | 2026-08-20 | Peter | PR #728 attached; no comments
3 | Done on our side — awaiting approval | KS-678 |  |  | #568 publishes 17 URLs on secuura.io — an unresol… | P2 | In Progress | Kam | n/a (rides #568) | n/a | 2026-08-21 | Peter (accept example.com host) / lands with #568 | Fix pushed on #568's base, folded into the custody branch; host choice offered to Peter | moved — now In Review / Kam (07:24Z)
3 | Done on our side — awaiting approval | KS-688 |  |  | run-in-slot.sh locks per worktree, not per slot —… | P2 | Tested Not Deployed | Kam | FULL 2026-08-28 (SET on develop, KS-685) | APPROVED 08-28 | 2026-08-28 | Kam (deploy) | #749 merged 08-28
3 | Done on our side — awaiting approval | KS-700 |  |  | Akto harness prints a FALSE ZERO when its Mongo c… | P2 | Tested Not Deployed | Kam | PARTIAL (Akto test:pr PASS + unit) | condition discharged; approval not evid. | 2026-09-01 | Kam (deploy) | #752; Peter's merge condition discharged with a real failure
3 | Done on our side — awaiting approval | KS-702 |  |  | Akto `quality` gate is RED on develop — format:ch… | P2 | Tested Not Deployed | Kam | FULL 2026-08-28 (Sch pr FAIL 6 pre-existing · Akto PASS · PW · k6 5/5) | review answered; approval not evid. | 2026-08-28 | Kam (deploy) | #754; Peter's four review points answered
3 | Done on our side — awaiting approval | KS-703 |  |  | Security: a NUL byte in a query param 500s and le… | P2 | In Review | Kam | UNKNOWN | APPROVED 08-31 | 2026-09-01 | Kam (deploy) | #757 merged 08-31; 'merged is not deployed'
3 | Done on our side — awaiting approval | KS-705 |  |  | Anchoring is idempotent on the row but not on the… | P2 | In Review | Kam | UNKNOWN | APPROVED (inferred, KS-703) | 2026-08-31 | Kam (deploy) | #756 (KS-703 note: 'both merged on Peter's approval')
3 | Done on our side — awaiting approval | KS-706 |  |  | systemTest/performance quality gate is RED on dev… | P2 | Tested Not Deployed | Kam | NONE ('not run, stated on the PR') | NOT YET | 2026-08-28 | Kam (deploy) | #755
3 | Done on our side — awaiting approval | KS-712 |  |  | 173 routed /api endpoints are absent from the Ope… | P2 | In Review | Kam | UNKNOWN | REQUESTED | 2026-09-01 | Peter | PR #760; four parked findings filed
3 | Done on our side — awaiting approval | KS-715 |  |  | Akto result capture dies on ENOBUFS — execSync ha… | P2 | In Review | Kam | NONE (unit/lint only) | REQUESTED | 2026-08-28 | Peter | PR #759 on Peter
3 | Done on our side — awaiting approval | KS-719 | yes |  | Security: PUT /api/privacy/settings and /api/sett… | P2 | Deployed to UAT (archived) | Kam | FULL 2026-08-29 | APPROVED 08-29 | 2026-08-29 | Kam/Stuart (UAT accept) | #762 merged on Peter's verified approval, four suites run, live on demo 08-29
3 | Done on our side — awaiting approval | KS-727 |  |  | Security: errorHandler returns err.message verbat… | P2 | In Review | — | UNKNOWN | APPROVED (#767); #776 REQUESTED | 2026-09-01 | Peter (#776) | #767 merged 09-01 (at-head approval); #776 (class guard) open
3 | Done on our side — awaiting approval | KS-728 |  |  | POST /api/auth/social/link never responds - auth.… | P2 | In Review | — | UNKNOWN (Peter measured defect live 09-01) | APPROVED 09-01 | 2026-09-01 | Kam (deploy / accept) | #766 merged 09-01 on Peter's at-head approval
3 | Done on our side — awaiting approval | KS-742 |  |  | Security: GET /api/keys enumerates another tenant… | P2 | Deployed to UAT | Kam | NONE (justified: /api/keys unpublished) | APPROVED 09-01 | 2026-09-01 | Kam/Stuart (UAT accept) | Deployed to demo and verified; #770 merged on Peter's at-head approval
3 | Done on our side — awaiting approval | KS-743 |  |  | Security: the KS-742 tenancy fix left three live… | P2 | In Review | Kam | FULL* 2026-09-01 (SET ran; exercised 0 of the changed ops) | REQUESTED | 2026-09-01 | Peter | PR #778 (head bbafa5b6b) on Peter
3 | Done on our side — awaiting approval | KS-751 |  |  | Three HIGH advisories published 2026-09-01 block… | P2 | Backlog | — | UNKNOWN (preflight 9/9 only) | REQUESTED (#781) | 2026-09-01 | Peter (review #781) | PR #781 (script-mode gate) open on Peter; the actual bump is not started
3 | Done on our side — awaiting approval | KS-250 | yes |  | Schemathesis HTML Report: Flag method_not_allowed… | P3 | Todo (archived) | Peter | PARTIAL (Sch green) | n/a (Peter's) | 2026-07-22 | Peter (close) | #314 merged 06-23 'Done — archiving'; Peter's ticket
3 | Done on our side — awaiting approval | KS-419 | yes |  | Anchoring boots before its tables are migrated (w… | P3 | Deployed to UAT (archived) | Kam | UNKNOWN | not evidenced | 2026-08-14 | Kam/Stuart (UAT accept) | On demo since the 08-14 Kintsugi deploy; archived 08-14
3 | Done on our side — awaiting approval | KS-472 | yes |  | NUL/control bytes are accepted AND persisted on 1… | P3 | Deployed to UAT (archived) | Kam | UNKNOWN | not evidenced | 2026-08-14 | Kam/Stuart (UAT accept) | On demo since the 08-14 Kintsugi deploy; archived 08-14
3 | Done on our side — awaiting approval | KS-480 |  |  | S↔K (K-side): support consistent user/org ownersh… | P3 | In Review | Kam | UNKNOWN | APPROVED w/ conditions 07-29 (§5/§6) | 2026-08-27 | Stuart (PS-319 close-out) / Kam (close) | K build complete (#610/#611); findings PR #672; Stuart's questions withdrawn
3 | Done on our side — awaiting approval | KS-508 |  |  | GET /api/documents/{id}/sig.json returns undocume… | P3 | In Review | Kam | FULL 2026-08-17 (CI checks green at merge) | not evidenced | 2026-08-25 | Peter (sweep confirm) / Kam (close) | Merged (#710) + deployed to demo; needs one clean Sch sweep to close
3 | Done on our side — awaiting approval | KS-514 |  |  | POST /api/credentials → 500 INTERNAL_ERROR "Inval… | P3 | In Review | Kam | NONE (sweep not re-run) | REQUESTED | 2026-08-27 | Peter | PR #741 up
3 | Done on our side — awaiting approval | KS-539 |  |  | K: define governing rules for document operations… | P3 | In Review | Kam | n/a (doc) | APPROVED 08-05 | 2026-08-19 | Stuart (sign-off) | Kam + Peter signed off 08-05; Stuart's sign-off deliberately outstanding
3 | Done on our side — awaiting approval | KS-611 |  |  | POST /api/timestamps/batch errors on every sweep… | P3 | In Review | Peter | PARTIAL (Sch full sweep 09-01) | n/a (author) | 2026-09-01 | Peter (close) | Peter's ticket; merged 09-01, acceptance holds
3 | Done on our side — awaiting approval | KS-615 | yes |  | The Caddyfile is the demo's real TLS edge and is… | P3 | Deployed to UAT (archived) | Kam | UNKNOWN | not evidenced | 2026-08-14 | Kam/Stuart (UAT accept) | On demo since the 08-14 Kintsugi deploy; archived 08-14
3 | Done on our side — awaiting approval | KS-616 | yes |  | Rate limiter still fails open on error — the surv… | P3 | Deployed to UAT (archived) | Kam | UNKNOWN | not evidenced | 2026-08-14 | Kam/Stuart (UAT accept) | On demo since the 08-14 Kintsugi deploy; archived 08-14
3 | Done on our side — awaiting approval | KS-622 |  |  | POST /api/auth/mfa/verify redeems backup codes wi… | P3 | In Review | Kam | NONE (preflight only) | REQUESTED | 2026-08-26 | Peter | PR #745 (option B as ruled) | moved — now Tested Not Deployed / Kam (08:38Z)
3 | Done on our side — awaiting approval | KS-645 |  |  | Security: POST /api/rate-limit/reset has no role… | P3 | In Review | Kam | NONE (preflight only) | REQUESTED | 2026-08-27 | Peter | PR #739 up
3 | Done on our side — awaiting approval | KS-646 |  |  | The `!test-wallet.env` negation makes the hardeni… | P3 | In Review | Kam | NONE (not run) | REQUESTED | 2026-08-26 | Peter | PR #740 up
3 | Done on our side — awaiting approval | KS-654 |  |  | frontend/demo-overlay ships an untracked, unversi… | P3 | In Review | Kam | FULL 2026-08-17 (CI: k6·PW·Sch·Akto) | not evidenced | 2026-08-17 | Kam (close) | Merged (#713) on all pr jobs green; local-only, no deploy
3 | Done on our side — awaiting approval | KS-659 |  |  | api-gateway spec hot-reload never fires in the co… | P3 | In Review | — | UNKNOWN | not evidenced | 2026-08-31 | Kam (close) | #718 merged 09-01 (per KS-611 note) | moved — now In Review / — (08:51Z)
3 | Done on our side — awaiting approval | KS-680 |  |  | validate-env.sh stops at its first main-body erro… | P3 | In Review | Kam | NONE (preflight only) | APPROVED 08-31 | 2026-08-31 | Kam (close) | #743 merged 08-31; no deployable surface
3 | Done on our side — awaiting approval | KS-689 |  |  | POST /api/users/admin/create is mounted without a… | P3 | Tested Not Deployed | Kam | FULL 2026-08-28 (SET on develop, KS-685) | APPROVED 08-28 (relayed set) | 2026-08-28 | Kam (deploy) | #748 merged 08-28
3 | Done on our side — awaiting approval | KS-711 |  |  | systemTest/akto + systemTest/performance quality… | P3 | In Review | Kam | UNKNOWN | NOT YET | 2026-08-28 | Peter | PR #758 attached; no comments
3 | Done on our side — awaiting approval | KS-721 |  |  | Anchor schema: accept and anchor platform-s's opa… | P3 | In Review | Kam | FULL 2026-08-31 (Sch FAIL 8/311=baseline · Akto PASS · PW PASS · k6 5/5) | REQUESTED | 2026-08-31 | Peter (PR) + Stuart (deploy gate) | PR #763 on Peter; deploy gate is Stuart's (S crypto-shred commitment)
3 | Done on our side — awaiting approval | KS-726 |  |  | Write-ahead the Cardano tx hash: persist the dete… | P3 | In Review | Kam | UNKNOWN | APPROVED 09-01 | 2026-09-01 | Kam (merge-set) | #764 approved by Peter at 035f9b450; not merged
3 | Done on our side — awaiting approval | KS-303 | yes |  | RS256-align legacy/non-canonical deploy paths (KS… | P4 | In Review (archived) | — | UNKNOWN | not evidenced | 2026-06-23 | Kam (close) | #310 merged 06-23; archived

## Summary + legend
Platform K — open tickets by category | generated 2026-09-02 19:00 AEST from report v3 (board read 18:52 AEST, all 238 rows live)
Rows | 238
Category 1 — in our hands, ready to action (still open) | 123
Category 2 — requires input | 51
Category 3 — done on our side, awaiting approval | 61
Closed today (kept in the sheet, marked) | 3
Kam's percentage | 131 open tickets assigned to Kam; 67 (51%) need nobody outside Kam, Wednesday and the agents (category 1). Was 71/132 = 54% at 17:30.
Column | Meaning
Category | 1 = ours to action now · 2 = needs input from Kam/Peter/Stuart/HP · 3 = done on our side, waiting for review/approval/close
Four-suite evidence | Whether the four platform suites (Schemathesis · Akto · Playwright · k6) are evidenced as ONE run on the ticket's PR or merged tree. FULL = all four with a date · PARTIAL = some (named; Sch = Schemathesis, PW = Playwright) · NONE = a PR exists with no run recorded · UNKNOWN = a PR exists but evidence not found in Linear · n/a (no PR) = no code change to test
Peter's review | Whether PeterObeden's approval of the PR is recorded: approved <date> · not evidenced (PR exists, no approval found) · n/a (no PR, or Peter is the author)
Waiting on / approval from | Category 2: who must answer. Category 3: whose approval or acceptance closes it
Movement today | State/assignee change since the 16:51 read, with the time (UTC)
Archived | Removed from the board view by an issue-cap cull, workflow state unchanged — archived is not Done
Note (categories 1–3 rules) | 1 = unassigned or assigned to Kam's Secuura account and no open question in the newest comments; the sort inside each category is priority then identifier